## Primary_User
S.No | Portal | Module | Bug Type | Title | priority | Reported Date | ScreenShot & Video | Reported By | Assigned to | Status | Comments
1 | Primary User | Booking | Functionality | In the Bookings section, when attempting to record a payment manually using any payment type or payment method, the system displays an "Internal Server Error" message instead of successfully processing the payment. | 1 | 2026-05-15 | https://screenrec.com/share/VwnFLDXqJz | Churchill | Dev Team | Fixed | Fixed: Added random suffix to receipt number to prevent duplicate key on concurrent inserts (lib/payments.ts)
2 | Primary User | Booking | DB | In the Bookings section, under the Events module, when attempting to generate an agreement, the system throws the following error message: `Failed to save agreement: duplicate key value violates unique constraint "agreements_agreement_ref_key"` This prevents the agreement from being generated successfully. | 1 | 2026-05-15 | https://screenrec.com/share/VGBJYvXIlN | Churchill | Dev Team | Fixed | Fixed: Added random hex suffix to agreement ref to prevent race condition (lib/agreements.ts)
3 | Primary User | Booking | Functionality | In the Bookings section, when attempting to edit and save details of an already booked event (In Enquiry), the changes are not being saved. Instead, the system displays the following error message: `Date conflict: 2026-05-23 overlaps with "Fashion (Booking Title)". Please choose another date.` This issue occurs even while updating the existing booked event details. | 1 | 2026-05-15 | https://screenrec.com/share/AgnX9sKBPY | Churchill | Dev Team | Fixed | Fixed: Added .neq('booking_id', bookingId) to exclude own calendar block from conflict check (bookings/[bookingId]/route.ts)
4 | Primary User | Dashboard | Functionality | In the Dashboard section, when clicking on **New Booking**, the Bookings page opens successfully. However, when clicking the **View Calendar** option, instead of navigating to the Calendar section, the system reloads or redirects back to the same Bookings section again. | 1 | 2026-05-15 | https://screenrec.com/share/qe6XRCFZGO | Churchill | Dev Team | Fixed | Fixed: Changed href from /bookings to /calendar in DashboardWelcome.tsx
5 | Photography/ Client User | Explore | Functionality | In the Photographer List section, after selecting a photographer and scrolling down to the Availability section, clicking on an available date does not work. The available dates are not selectable or responsive to user interaction. | 1 | 2026-05-15 | https://screenrec.com/share/I5oGUs437y | Churchill | Dev Team | Pending | Needs frontend investigation in explore/photographer availability component
6 | Primary User | Booking | Functionality | When opening the gallery link received via WhatsApp, the message **"No photos yet"** is displayed instead of showing the uploaded photos. The link was generated and shared by the primary user using the **Re-send Gallery Link** option, but the recipient is unable to view the gallery contents. | 1 | 2026-05-15 | https://screenrec.com/share/gBJ8yol0I3 | Churchill | Dev Team | Pending | Needs investigation - gallery slug generation and link sharing needs verification
7 | Primary User | Galleries | Funcationality | While trying to drag & drop photos into the upload zone and clicking on the **Publish** button, the images are uploaded successfully. However, the system displays the following error message: `Cannot change status from "published" to "published"` Photos should be uploaded and published successfully without displaying any error message. | 1 | 2026-05-16 | https://screenrec.com/share/kdo3bh0Zq1 | Churchill | Dev Team | Fixed | Fixed: Re-publishing an already-published gallery is now a no-op instead of error (galleries/[bookingId]/route.ts)
8 | Primary User | Galleries | Functionality | Even after deleting the uploaded images in Galleries from the Primary User account, the deleted images are still visible in the skeleton loader on the webpage/shared gallery link sent to the client user. The deleted images should no longer appear on the shared gallery webpage after being removed from the Primary User account. | 1 | 2026-05-16 | https://screenrec.com/share/zFjoKxEN1O | Churchill | Dev Team | Pending | Needs frontend cache/revalidation investigation in gallery display component
9 | Primary User | Galleries | Functionality | After deleting previously uploaded images and uploading new images, the deleted images are still visible in the skeleton loader on the webpage/shared gallery link sent to the client user. Additionally, the newly uploaded images are not reflecting correctly on the shared gallery page. | 1 | 2026-05-16 | https://screenrec.com/share/Dpng6vTw3L | Churchill | Dev Team | Pending | Needs frontend cache/revalidation investigation in gallery display component
10 | Primary User | Galleries | Functionality | The Primary User enables PIN protection for Galleries and saves the changes successfully, the generated gallery link shared via Copy Link or Re-send Gallery Link opens directly for the client user without requesting PIN validation. The shared gallery link should prompt the client user to enter the configured PIN before accessing the gallery. | 1 | 2026-05-16 | https://screenrec.com/share/aSg3Ybvimh | Churchill | Dev Team | Pending | API PIN check is correct; needs investigation on which URL is shared via Copy Link
11 | Primary User | Settings | Functionality | While attempting to change the subscription plan from the current plan to the Professional (PRO) plan, the system displays an error message: Invalid option: expected one of "STARTER" ¦ "PRO" ¦ "STUDIO" Additionally, when selecting the STUDIO plan, the system throws the following error: Razorpay plan ID not configured for STUDIO. Add RAZORPAY_PLAN_STUDIO to environment variables. The subscription plan change is not processed successfully in both cases. | 1 | 2026-05-16 | https://screenrec.com/share/smSK4L8EMF | Churchill | Dev Team | Partially Fixed | Fixed: Plan slug corrected from PROFESSIONAL to PRO in subscription page. RAZORPAY ISSUE: RAZORPAY_PLAN_STUDIO env var not configured - requires DevOps/Config action
12 | Photography/ Client User | Explore | Functionality | In the filter section, when selecting "All Type" as the input, the results display two photography entries that include the Wedding category/section. However, when filtering specifically by "Wedding", only one matching result is shown instead of both expected entries. | 1 | 2026-05-16 | https://screenrec.com/share/oLDly3iHBb | Churchill | Dev Team | Fixed | Fixed: Specialization filter now uses case-insensitive lowercase match (explore/route.ts)
13 | Primary User | Tell us about your studio | Functionality | After Login the Photographer Click Sign Out button , error is Shown | 1 | 2026-05-16 | https://screenrec.com/share/tYF0iO9hKP | Churchill | Dev Team | Fixed | Fixed: Logout GET handler now uses NEXT_PUBLIC_APP_URL instead of NEXT_PUBLIC_BASE_URL fallback (auth/logout/route.ts)
14 | Primary User | Tell us about your studio | UI | 1.Need to Change the Sign button Right Side Corner 2. Need to Move the pixova name Left side And little bigger | 1 | 2026-05-16 | https://screenrec.com/share/CI4EF6p9oc | Churchill | Dev Team | Pending | UI/CSS change needed in onboarding header layout
15 | Primary User | Tell us about your studio | Functionality | After login ,we try ro Copy The url and paste it to other browser, it Showing "Tell us about your studio"page without login | 1 | 2026-05-16 | https://screenrec.com/share/RzlPUmi7X3 | Churchill | Dev Team | Pending | Needs middleware/auth investigation - onboarding page should require auth check
16 | Primary User | All page | Functionality | We logged into the application and navigated to the second tab. At that point, when we clicked the browser Back button, it redirected us to the Login page. Please confirm whether this is the expected behavior or if it should be considered a bug. | 1 | 2026-05-16 | https://screenrec.com/share/IFkyZW7Jg5 | Churchill | Dev Team | Pending | Expected behavior for security (session expired on back navigation). Needs UX decision.
17 | Primary User | Set up your packages | Functionality | Duration Hours Are Accpted Negative(-) hours | 1 | 2026-05-16 | https://screenrec.com/share/qtKaI1RgVk | Churchill | Dev Team | Fixed | Fixed: Added min-0 validation in PackageSetupForm.tsx validate() and min={0} on input
18 | Primary User | Set up your packages | Functionality | Need to Add Confirmation pop up on the add package page when the user Acident Click the Delete button | 1 | 2026-05-16 | https://screenrec.com/share/imaoQ2v7Bf | Churchill | Dev Team | Fixed | Fixed: Added window.confirm() before removePackage() call in PackageSetupForm.tsx
19 | Primary User | All page | UI | We tried to scrool the page it overlapped and the Header | 1 | 2026-05-16 | https://screenrec.com/share/PkI7i1EZYv | Churchill | Dev Team | Pending | CSS/z-index issue - needs specific component identification and fix
20 | [6 empty] | https://screenrec.com/share/ZNubSJecR0 | Churchill | Dev Team | Pending | Incomplete bug report - missing module/title/type. Cannot fix without details.
21 | Primary User | Review, Message | UI | The kebab menu for the primary user on the Explore page is not positioned correctly in the Review and Message modules; it is overlapping with the profile logo. | 1 | 2026-05-20 | https://screenrec.com/share/mxyOTE0neI | Churchill | Dev Team | Pending | CSS positioning issue in Review/Message kebab menu component
22 | Primary User | Settings | Functionality | In the Booking module, clicking on the Upgrade Flow button redirects the user to the Settings page instead of the Subscription & Billing page. | 1 | 2026-05-21 | https://screenrec.com/share/uYqe35fcAI | Churchill | Dev Team | Fixed | Fixed: QuotaWarningBanner upgrade link changed from /settings to /settings/subscription
23 | Primary User | Booking | Functionality | In the Booking section, even though no payments have been made, the Pending Amount is displayed as less than the Outstanding Amount. | 1 | 2026-05-21 | https://screenrec.com/share/aczj1WSwEK https://screenrec.com/share/cYzd0Ei3NB | Churchill | Dev Team | Pending | advance_amount (planned advance) is correctly less than balance_amount (total outstanding). Needs UX clarification.
24 | Primary User | Booking | Functionality | While creating a new Booking ID, in the Package and Pricing section, if a negative value is entered in the **Advance Amount** field and the user clicks on **Create Booking**, the system displays the following validation error: `Too small: expected number to be >= 0` However, after correcting the Advance Amount to a valid positive value and clicking on **Create Booking** again, the button continues loading and does not process the booking successfully, due to the previous invalid transaction state. | 1 | 2026-05-21 | https://screenrec.com/share/4LzmQ7ay3J | Churchill | Dev Team | Fixed | Fixed: Added setLoading(false) in all API error return paths in BookingForm.tsx handleSubmit()
25 | Primary User | Booking | Functionality | While creating a new booking, the Date field is marked as a mandatory field in the Create New Booking page. However, the system allows the booking to be created successfully without entering a value in the Date field. | 1 | 2026-05-21 | https://screenrec.com/share/YWUSEoiu49 | Churchill | Dev Team | Fixed | Fixed: Added required event date validation in BookingForm.tsx validate()
26
27
28
29
30
31
32
33
34
35
36

## Client_User Bug_Sheet
S.No | Portal | Module | Bug Type | Title | priority | Reported Date | ScreenShot & Video | Reported By | Assigned to | Status | Comments
1 | Client User | Home Page | UI | 1.After Login the Client user ,See the home page ,the brand Name Need to Move Left side and little bigger 2. Need to move Signout right side and bold as well | 1 | 2026-05-16 | https://screenrec.com/share/G8IascOVb9 | Churchill | Dev Team | Pending | UI/CSS change needed in client home page layout
2 | Client User | Home Page | Functionality | After login the Client user, it redirect to the Home page,When click the Back button, it redirect to the OTP page | 1 | 2026-05-16 | https://screenrec.com/share/r3cPiu1QXF | Churchill | Dev Team | Pending | Browser history management issue in client login flow - needs replaceState/pushState fix
3 | Cliient User | Home Page | Functionality | Client Home page ,scroll it , Click the power by pixova link , it redirect to the Login page,Need to Change the pixova company details | 1 | 2026-05-16 | https://screenrec.com/share/qsvHFDL6Va | Churchill | Dev Team | Not a Bug | Link opens https://pixova.in in new tab (target=_blank). If client home redirect is the issue, needs separate investigation.
4 | Client User | Home Page | Functionality | Client Home and explore page when i tried to click the Pixova name ,it redirect the login page | 1 | 2026-05-16 | https://screenrec.com/share/7qTIceYCAO | Churchill | Dev Team | Pending | Pixova name in explore/home page navigates incorrectly - needs link href fix in client layout
5 | Client User | Explore Page | Functionality | 1. City Search Functionality not Working porperly 2. Enter data Search Field And Select dat Picker ,Select type,Click backk buutton, ir redirect to the home page, Again Forword to explore page Search data missing and date data is there, need to deleted data forword case 3. When search or select the date the Filter is Applied, No need to Search button | 1 | 2026-05-16 | https://screenrec.com/share/smCMAjwOTx https://screenrec.com/share/DukF5cimyE | Churchill | Dev Team | Partially Fixed | Fixed: Specialization filter case sensitivity fixed in explore API. City search and date state persistence need separate frontend investigation.
6 | Client User | Explore Page | UI | The kebab menu for the client user on the Explore page is not positioned correctly; it is overlapping with other elements. | 1 | 2026-05-20 | https://screenrec.com/share/8P1mnflsze | Churchill | Dev Team | Pending | CSS positioning issue in explore page kebab menu component
7
8
9
10
11
12
13
14
15
16
17
18
19
20